## Sheet
AIUK COMMUNITY PLATFORM TIMELINE
PHASE |  | DELIVERABLES | Q1 |  |  |  |  | Q2 | [12 empty] | Q1 2026 | [12 empty] | Q2 2026
|  |  | SEP |  |  |  |  | OCT |  |  |  | NOV |  |  |  | DEC |  |  |  |  | JAN |  |  |  | FEB |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  | JUNE
|  | Sprint # based on WAO start date --> |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19 |  | 20 |  | 21 |  | 22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | 29 |  | 30 |  | 31 |  | 32 |  | 33 |  | 34
| PROJECT PHASE: | First Monday of each month --> | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29
1 | Planning and Preparation | Confirm project plan and roadmap
Mapping mini user journeys within community platform
Documentation for hosting and integration roadmap
Pilot phase plan document, including community metrics.
Brief for configuration of the platform
Training Plan
| Pilot activities | RECRUITMENT
2 | Pilot Build | Configured Pilot Platform
Onboarding Flow and Training Materials
Pilot Community Guidelines and CoC
Pilot Recognition Ecosystem
| Pilot activities | TESTING | bar: 3 to 24
INFORMATION SESSIONS
3 | Pilot Launch and Iteration | Usage reports including sentiment analysis.
Co-create a scalable community management plan
Final evaluation report
Full Training Programme Guide
| Pilot Phase | TRAINING
PILOT PHASE 1
PILOT PHASE 2
PILOT PHASE 3
4 | Adjust and Public Launch | A public-facing platform with membership management, moderation and user roles.
Project documentation with index.
Refined Onboarding Kit
| Pilot Phase | PILOT PHASE 4
IMPLEMENTATION